## Sheet1
JYOTHY INSTITUTE OF TECHNOLOGY
PROJECT WORK BREAK DOWN STRUTCTURE
PROJECT TITLE : FAST IP ROUTING IN WIRELESS SENSOR NETWORK
| DATE : |  | PALLAVI AITHAL N | VAISHNAVI B
MILESTONE 1 : DISCUSSING ABOUT TITLE
| 2016-09-16 |  | Project Title Discussion | Project Title Discussion
| 2016-09-17 |  | Routing | Types of Routing
| 2016-09-18 |  | Routing Protocols | Protocols
| 2016-09-19 |  | Static Routing | Dynamic Routing
| 2016-09-20 |  | Process of Routing | Process of Routing
| 2016-09-21 | ENGINEERS DAY & CORONA LABS EVENT (copter game)
2016-09-22
2016-09-23
2016-09-24
| 2016-09-25 | SUNDAY
| 2016-09-26 |  | Surfing about IP Routing | OSI Layer
| 2016-09-27 |  | TCP/IP Layer | IPV 4
| 2016-09-28 |  | IPV6 | IPV6
| 2016-09-29 |  | Comparison b/w IPV4 and IPV6 | Comparison b/w IPV4 and IPV6
| 2016-09-30 |  | LAN | WAN
| 2016-01-10 | INTERNALS
2016-06-10
2016-07-10
2016-08-10
| 2016-09-10 | SUNDAY
| 2016-10-10 | DUSSERA HOLIDAYS
16/10/2016
| 17/10/2016 |  | Preparing SRS Documents | Workbreakdown Structure
| 18/10/2016 |  | Absract | Project Dairy
| 19/10/2016 |  | PM primer event | Installation of VM wear
| 20/10/2016 |  | NTT Data Placement | Meeting with guide
| 21/10/2016 |  | Meeting with guide | Preperation for review
| 22/10/2016 |  | Verifying project document with guide | Verifying project document with guide
| 23/10/2016 |  | Referring RFC5714 | Referring RFC5714
24/10/2016
25/10/2016
MILESTONE 2: LEARNING NS2 AND NS3
| 26/10/2016 |  | Learning TCL Script | Using Wireshark
27/10/2016
28/10/2016
29/10/2016
30/10/2016
31/10/2016
2016-01-11
2016-02-11
2016-03-11
2016-04-11
2016-05-11
2016-06-11
2016-07-11
| 2016-08-11 |  | INTERNALS
2016-09-11
2016-10-11
2016-11-11
2016-12-11
13/11/2016
14/11/2016
15/11/2016
16/11/2016
| 17/11/2016 |  | Using Wireshark | Learning TCL Script
18/11/2016
19/11/2016
20/11/2016
21/11/2016
22/11/2016
23/11/2016
24/11/2016
25/11/2016
26/11/2016
27/11/2016
28/11/2016
29/11/2016
| 30/11/2016 |  | TSE ABOUT JDBC | TSE ABOUT JDBC
2016-01-12
2016-02-12
| 2016-03-12 |  | Analysing Optimal number of nodes | Analysing Micro loops
2016-04-12
2016-05-12
2016-06-12
2016-08-12
| 2016-09-12 |  | EXTERNAL EXAMINATION
2016-10-12
2016-11-12
2016-12-12
13/12/2016
14/12/2016
15/12/2016
16/12/2016
17/12/2016
18/12/2016
19/12/2016
20/12/2016
21/12/2016
22/12/2016
23/12/2016
24/12/2016
25/12/2016
26/12/2016
27/12/2016
28/12/2016
29/12/2016
30/12/2016
2017-01-01
14/1/2017
| 15/1/2017 |  | Installation of ns-2 | Installation of ns-2
| 20/1/2017 |  | literarature survey: papers on | Literature survey: papers on
21/1/2017
22/1/2017
23/1/2017
24/1/2017
25/1/2017
26/1/2017
27/1/2017
| 28/1/2017 |  | algorithm for topology identification | implementing code for topology
29/1/2017
30/1/2017
31/1/2017
2017-01-02
2017-02-02
2017-03-02
2017-04-02
2017-05-02
2017-06-02
2017-07-02
2017-08-02
2017-09-02
| 2017-10-02 |  | MILESTONE 3: IMPLEMENTATION OF TOPLOLOGY IDENTIFICATION
2017-11-02
| 2017-12-02 |  | creation of nodes in ns2 | code for setting node attributes in ns2
13/2/2017
14/2/2017
15/2/2017
16/2/2017
17/2/2017
18/2/2017
19/2/2017
20/2/2017
21/2/2017
22/2/2017
23/2/2017
24/2/2017
25/2/2017
26/2/2017
27/2/2017
28/2/2017
| 2017-01-03 |  | implementing sleep/wake function | algorithm for spanning tree
2017-02-03
2017-03-03
2017-04-03
2017-05-03
2017-06-03
2017-07-03
2017-08-03
2017-09-03
2017-10-03
| 2017-11-03 |  | testing sleep/wake function | implementing spanning tree algorithm
2017-12-03
13/3/2017
14/3/2017
15/3/2017
16/3/2017
| 17/3/2017 |  | TECHINAL SEMINAR REVIEW-1
18/3/2017
19/3/2017
| 20/3/2017 |  | 1ST INTERNALS
21/3/2017
22/3/2017
24/3/2017
25/3/2017
26/3/2017
27/3/2017
28/3/2017
29/3/2017
30/1/2017
31/1/2017
2017-01-04
2017-02-04
2017-03-04
2017-04-04
2017-05-04