## Sheet1
JYOTHY INSTITUTE OF TECHNOLOGY
PROJECT WORK BREAK DOWN STRUTCTURE
PROJECT TITLE : FAST IP ROUTING IN WIRELESS SENSOR NETWORK
| DATE : |  | PALLAVI AITHAL N | VAISHNAVI B
MILESTONE 1 : DISCUSSING ABOUT TITLE
| 2016-09-16 |  | Project Title Discussion | Project Title Discussion
| 2016-09-17 |  | Routing | Types of Routing
| 2016-09-18 |  | Routing Protocols | Protocols
| 2016-09-19 |  | Static Routing | Dynamic Routing
| 2016-09-20 |  | Process of Routing | Process of Routing
| 2016-09-21 | ENGINEERS DAY & CORONA LABS EVENT (copter game)
2016-09-22
2016-09-23
2016-09-24
| 2016-09-25 | SUNDAY
| 2016-09-26 |  | Surfing about IP Routing | OSI Layer
| 2016-09-27 |  | TCP/IP Layer | IPV 4
| 2016-09-28 |  | IPV6 | IPV6
| 2016-09-29 |  | Comparison b/w IPV4 and IPV6 | Comparison b/w IPV4 and IPV6
| 2016-09-30 |  | LAN | WAN
| 2016-01-10 | INTERNALS
2016-06-10
2016-07-10
2016-08-10
| 2016-09-10 | SUNDAY
| 2016-10-10 | DUSSERA HOLIDAYS
16/10/2016
| 17/10/2016 |  | Preparing SRS Documents | Workbreakdown Structure
| 18/10/2016 |  | Absract | Project Dairy
| 19/10/2016 |  | PM primer event | Installation of VM wear
| 20/10/2016 |  | NTT Data Placement | Meeting with guide
| 21/10/2016 |  | Meeting with guide | Preperation for review
| 22/10/2016 |  | Verifying project document with guide | Verifying project document with guide
| 23/10/2016 |  | Referring RFC5714 | Referring RFC5714
24/10/2016
25/10/2016
MILESTONE 2: LEARNING NS2 AND NS3
| 26/10/2016 |  | Learning TCL Script | Using Wireshark
27/10/2016
28/10/2016
29/10/2016
30/10/2016
31/10/2016
2016-01-11
2016-02-11
2016-03-11
2016-04-11
2016-05-11
2016-06-11
2016-07-11
| 2016-08-11 |  | INTERNALS
2016-09-11
2016-10-11
2016-11-11
2016-12-11
13/11/2016
14/11/2016
15/11/2016
16/11/2016
| 17/11/2016 |  | Using Wireshark | Learning TCL Script
18/11/2016
19/11/2016
20/11/2016
21/11/2016
22/11/2016
23/11/2016
24/11/2016
25/11/2016
26/11/2016
27/11/2016
28/11/2016
29/11/2016
| 30/11/2016 |  | TSE ABOUT JDBC | TSE ABOUT JDBC
2016-01-12
2016-02-12
| 2016-03-12 |  | Analysing Optimal number of nodes | Analysing Micro loops
2016-04-12
2016-05-12
| 2016-06-12 |  | Working with Topologies
| 2016-08-12 |  |  | Analysing Existing Algorithms
2016-09-12
2016-10-12
2016-11-12
2016-12-12
13/12/2016
14/12/2016
| 15/12/2016 |  | Learning about Repairing Path
16/12/2016
17/12/2016
18/12/2016
19/12/2016
20/12/2016
21/12/2016
22/12/2016
23/12/2016
24/12/2016
25/12/2016
26/12/2016
| 27/12/2016 |  | Implementing Algorithms | Implementing Algorithms
28/12/2016
29/12/2016
| 30/12/2016 |  | EXTERNALS
2017-01-01
14/1/2017